Distr.

LIMITED

CS/CMI/FSDSSC/XV/3

November 2021

Original:   ENGLISH

# COMMON MARKET FOR EASTERN

AND SOUTHERN AFRICA

15th Meeting of the COMESA Financial System

Development and Stability Sub-Committee

## 25th November, 2021

Virtual Meeting

REPORT BY MEMBER COUNTRIES ON THE IMPLEMENTATION OF THE COMESA ASSESSMENT FRAMEWORK FOR FINANCIAL SYSTEM STABILITY IN 2020

2021 (IZ/LN/TB-joo)

Status of Implementation of the COMESA Financial Stability Assessment Framework by the 13 Member States

| No. | Task | Activity | Completion Date | Status of Implementation |
| --- | --- | --- | --- | --- |
|  |  |  |  | Implemented | Work In Progress | Not Implemented |
| 1 | Financial Stability Unit | Establish a Financial Stability Unit | June 2020 | Burundi D R Congo Egypt Eswatini Kenya Mauritius Seychelles Sudan Uganda |  |  |
| 2 | Financial Stability Committee | Establish a multi-disciplinary Financial Stability Committee | June 2020 | Burundi Egypt Eswatini Kenya Mauritius Seychelles Sudan Uganda. | D R Congo |  |
| 3 | Action Plan | Develop in-country Action Plan for Implementation of COMESA Framework covering: |
|  | Development of capacity on sound Macro-prudential analysis | June 2020 | Seychelles Uganda Mauritius Kenya Eswatini Egypt D R Congo Burundi | Sudan |  |
|  | Institutional Framework to translate financial stability analysis to policy making | June 2020 | Burundi D R Congo Egypt Eswatini Kenya Mauritius Uganda | Sudan | Seychelles |
|  | Undertake work to determine Domestic Systematically Important Banks (DSIB’s) and design appropriate policies to manage risks that could be posed by these institutions | June 2020 | Burundi D R Congo Egypt Eswatini Kenya Mauritius Uganda | Sudan | Seychelles |
|  | Forward Looking Financial stability reports | June 2020 | Egypt Eswatini Kenya Mauritius Seychelles Sudan Uganda. | Burundi D R Congo |  |
|  | Implementation of macro-prudential policies | June 2020 | Burundi Sudan Uganda Mauritius Kenya Eswatini Egypt D R Congo | Seychelles |  |
|  | Institutional arrangements which specify responsibilities, powers and inter agency coordination to undertake macro-prudential surveillance. The institutional arrangements should merge all the key aspects of the financial system, including banking institutions, the insurance and pension sector, financial markets and payment systems | June 2020 | Burundi Seychelles Sudan Uganda Mauritius Kenya Eswatini Egypt D R Congo |  |  |
| 4 | Submission of Forward-Looking Financial Stability Reports | Electronic submission of Financial Stability Assessment Reports to the Secretariat for posting onto the COMESA website | June 2020 | Burundi Seychelles Uganda Mauritius Kenya Eswatini Egypt D R Congo | Sudan |  |
| 5 | Financial Soundness Indicators | Electronic submission of IMF Financial Soundness Indicators (FSIs) for banking sector to the Secretariat for posting onto the COMESA website | December 2019 | Burundi Seychelles Sudan Uganda Mauritius Kenya Eswatini Egypt D R Congo |  |  |
| 6 | Compliance to the Revised Basel Core Principles | Report on Compliance based on Revised Core Principles | June 2020 | Burundi Sudan Uganda Mauritius Kenya Eswatini Egypt D R Congo | Seychelles |  |

# Footnotes

This requires clarity in overall/final objective/mandate of macroprudential policy, identification of key risks/triggers, mapping, monitoring indicators and stress testing and having a robust policy toolkit/instrument including counter cyclical buffers.